## Sheet1
4 Week Schedule #12115 Cedar Ridge HS CTE Renovation
Sub | Description | 2022-07-25 | 2022-07-26 | 2022-07-27 | 2022-07-28 | 2022-07-29 | 2022-07-30 | 2022-07-31 | 2022-08-01 | 2022-08-02 | 2022-08-03 | 2022-08-04 | 2022-08-05 | 2022-08-06 | 2022-08-07 | 2022-08-08 | 2022-08-09 | 2022-08-10 | 2022-08-11 | 2022-08-12 | 2022-08-13 | 2022-08-14 | 2022-08-15 | 2022-08-16 | 2022-08-17 | 2022-08-18 | 2022-08-19 | 2022-08-20 | 2022-08-21
|  | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S
Sisk-Robb Inc
Duvall Electric | setting temp panel ac connect | bar: 2022-07-27 to 2022-07-29; 2022-08-01 to 2022-08-04
B&L Construction | ceiling grid and tile | bar: 2022-08-01 to 2022-08-05; 2022-08-08 to 2022-08-10
Kinney's Commercial Inc | run gas lines | bar: 2022-08-02 to 2022-08-05; 2022-08-08 to 2022-08-09
M-Tech | connect units start up | bar: 2022-07-25 to 2022-07-29; 2022-08-01; 2022-08-08 to 2022-08-12
Capitol Sprinkler&Fire Systems | reroute sprinkler lines | bar: 2022-08-08 to 2022-08-12
x
Ace Audio Communications Inc | speakers | bar: 2022-08-08 to 2022-08-10
Convergence Cabling | data drops | bar: 2022-07-28 to 2022-07-29
JLT Ginther LLC
Mission Restaurant Supply | install vent hoods | bar: 2022-07-26 to 2022-07-29; 2022-08-01 to 2022-08-05
Georgetown Millworks | deliver and install millwork | bar: 2022-07-26 to 2022-07-29
Commercial Metal Products
Alamo Door Systems
Anchor Ventana
Moderncrete Concrete Design
Flooring Solutions | flooring
Mesquite Commercial LLC | tile
Slater Painting | paint second coat and finish | bar: 2022-07-25 to 2022-07-28; 2022-08-02 to 2022-08-05
Texas Roofing | curbs & drying in
Toman Brothers
centx masonr | fill in cmu @ roll-up door