## 2 Week Look-Ahead Schedule
3 WEEK LOOK-AHEAD SCHEDULE
Spicewood ES
|  | 2022-07-04 | 2022-07-05 | 2022-07-06 | 2022-07-07 | 2022-07-08 | 2022-07-09 | 2022-07-10 | 2022-07-11 | 2022-07-12 | 2022-07-13 | 2022-07-14 | 2022-07-15 | 2022-07-16 | 2022-07-17 | 2022-07-18 | 2022-07-19 | 2022-07-20 | 2022-07-21 | 2022-07-22
SUBCONTRACTOR - TASK |  | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri
Are
Set dumpsters
Area B
Airco corridor and classrooms inspection on plan East 500 corridor | bar: 2022-07-05
Airco inpecti duct above restroom A1 & A2 | bar: 2022-07-05
Airco insulate duct in classrooms and corridor 500 | bar: 2022-07-06 to 2022-07-09; 2022-07-11
| B&L ceiling grid 500 corridor | 2022-07-04: Pending material delivery due to ASI 3 change to Class A fire rated
Electrical inspection Restroom set A walls & ceiling | bar: 2022-07-05
B&L install drywall in A1 & A2 | bar: 2022-07-06 to 2022-07-07
Tape and float joints in restroom A2 | bar: 2022-07-07
Install Tile at restroom set D drinking fountain area | bar: 2022-07-05 to 2022-07-06; 2022-07-11 to 2022-07-16; 2022-07-18 to 2022-07-19
Install grout at restroom set D drinking fountain area | bar: 2022-07-07
Install ceramic tile in restroom set A1 & A2 | bar: 2022-07-07 to 2022-07-09; 2022-07-11 to 2022-07-15
Install RTU 5
Install fire safing to new steel reinforcement at RTU location
Covergience install ceiling devices
Install ceiling tile
Area A
Install duct on 400 wing classrooms and corridors | bar: 2022-07-16; 2022-07-18
| B&L install ceiling grid in corridor 200 running East and West | 2022-07-04: Pending material delivery due to ASI 3 change to Class A fire rated
Repair joist at RTU 4 | bar: 2022-07-05
Install roof decking and curb at RTU 4 location | bar: 2022-07-06
Airco install duct work for RTU 3 & 4 in library | bar: 2022-07-11 to 2022-07-13; 2022-07-16; 2022-07-18 to 2022-07-20
Insulate duct in library | bar: 2022-07-13 to 2022-07-14; 2022-07-20 to 2022-07-21
Reinforment for RTUs inspectied
Install fire safing to new steel reinforcement at RTU location
| Install ceiling grid in library and 300 wing | 2022-07-04: Pending material delivery due to ASI 3 change to Class A fire rated
Airco instrall above ceiling cassette units at Admin area | bar: 2022-07-06 to 2022-07-08
Airco pipe in refrigerant Line sets for C
M-Tech complete plumbing rough in C set | bar: 2022-07-05 to 2022-07-08
Electrical inspectian | bar: 2022-07-07
B&L Install blocking for accessories and install drywall RR C | bar: 2022-07-07 to 2022-07-09; 2022-07-11
Medel Painting tape and float 1st coat paint RR C | bar: 2022-07-11 to 2022-07-14
Covergience install ceiling devices
| B&L install ceiling balance of area A | 2022-07-04: Pending material delivery due to ASI 3 change to Class A fire rated
| Set RTUs 3 & 4 | 2022-07-04: Pending arrival
Area C
| Install curb for RTU 1 | 2022-07-04: Pending the district's contractor relocating refrigerant lines for walk in cooler below
| Steel supports for RTU 1 | 2022-07-04: Pending the district's contractor relocating refrigerant lines for walk in cooler below
Connect power and controls to ehaust fans | bar: 2022-07-07 to 2022-07-09
Install ouside air duct in admini. Offices | bar: 2022-07-05 to 2022-07-07; 2022-07-21 to 2022-07-22
| B&L install ceiling grid | 2022-07-04: Pending material delivery due to ASI 3 change to Class A fire rated
B&L install FRL panels | bar: 2022-07-08 to 2022-07-09; 2022-07-11
Covergience install ceiling devices
B&L install ceiling tile
| Set RTU 1 & 2 | 2022-07-04: Pending arrival
Area D 100 wing
| B&L install corridor side of drywall | 2022-07-04: Pending resolution of new dicoveries after abatement demo
Medel tape ,float, prime and 1st coat corridor
M-Tech plumbing rough RR set B | bar: 2022-07-05 to 2022-07-09; 2022-07-11
Plumbing inspection | bar: 2022-07-11
B&L installl blocking and drywall | bar: 2022-07-08 to 2022-07-09; 2022-07-11 to 2022-07-12
Medel tape ,float, prime and 1st coat restrooms | bar: 2022-07-11 to 2022-07-13
| Set new CME | 2022-07-04: Pending arrival

## 3 Week Look-Ahead Schedule
3 WEEK LOOK-AHEAD SCHEDULE
ENTER PROJECT NAME HERE
|  | X = scheduled |  |  |  | D = delayed |  |  |  | H = holiday
|  | ENTER DATE | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
SUBCONTRACTOR - TASK |  | M | T | W | Th | F | Sa | Su | M | T | W | TH | F | Sa | Su | M | T | W | Th | F | Sa | Su