## 2 Week Look-Ahead Schedule
New Tech
2 week
|  | 2022-12-07 | 2022-12-08 | 2022-12-09 | 2022-12-10 | 2022-12-11 | 2022-12-12 | 2022-12-13 | 2022-12-14 | 2022-12-15 | 2022-12-16 | 2022-12-17 | 2022-12-18 | 2022-12-19 | 2022-12-20 | 2022-12-21 | 2022-12-22 | 2022-12-23 | 2022-12-24 | 2022-12-25 | 2022-12-26 | 2022-12-27 | 2022-12-28
SUBCONTRACTOR - TASK |  | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed
Utilities
| Install conduit for secondary power ( pending cost approva)l | 2022-12-07: Pending; 2022-12-08: Pending; 2022-12-09: Pending; 2022-12-12: Pending; 2022-12-13: Pending; 2022-12-14: Pending; 2022-12-15: Pending; 2022-12-16: Pending
| Fireline Pending underground permit approval | 2022-12-07: Pending; 2022-12-08: Pending; 2022-12-09: Pending; 2022-12-10: Pending; 2022-12-11: Pending; 2022-12-12: Pending; 2022-12-13: Pending; 2022-12-14: Pending; 2022-12-15: Pending; 2022-12-16: Pending
Concrete
Recieve rebar and void forms for grade beams | bar: 2022-12-08 to 2022-12-09
Install grade beam rebar | bar: 2022-12-12 to 2022-12-17
Form 2nd side of grade beam | bar: 2022-12-16 to 2022-12-17; 2022-12-19 to 2022-12-20
Install anchor bolts | bar: 2022-12-19 to 2022-12-21
Pour grade beams on grid lines A, I, and 1 | bar: 2022-12-21 to 2022-12-24
| Concrete for gride lines 10-11 Pending Fire riser, plumbing. Elec rough | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending | Pending
Plumbing
| Rough in domestic water and dry well ( pending #11 above) | 2022-12-07: Pending; 2022-12-08: Pending; 2022-12-09: Pending; 2022-12-10: Pending; 2022-12-11: Pending; 2022-12-12: Pending; 2022-12-13: Pending; 2022-12-14: Pending; 2022-12-15: Pending; 2022-12-16: Pending
Green is scheduled work
Pending
WP = weather permitting

## 3 Week Look-Ahead Schedule
3 WEEK LOOK-AHEAD SCHEDULE
ENTER PROJECT NAME HERE
|  | X = scheduled |  |  |  | D = delayed |  |  |  | H = holiday
|  | ENTER DATE | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
SUBCONTRACTOR - TASK |  | M | T | W | Th | F | Sa | Su | M | T | W | TH | F | Sa | Su | M | T | W | Th | F | Sa | Su