## 2 Week Look-Ahead Schedule
LOOK-AHEAD SCHEDULE
Spicewood ES |  | Spicewood ES
2022-08-01
|  |  | 2022-08-01 | 2022-08-02 | 2022-08-03 | 2022-08-04 | 2022-08-05 | 2022-08-06 | 2022-08-07 | 2022-08-08 | 2022-08-09 | 2022-08-10 | 2022-08-11 | 2022-08-12 | 2022-08-13
SUBCONTRACTOR - TASK |  | SUBCONTRACTOR - TASK | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat
Are
Set dumpsters
Airco( Duct)
Inspect balance of above ceiling | bar: 2022-08-01 to 2022-08-02
| #REF! | Final inspection | bar: 2022-08-03
| #REF! | Airco Piping
Final connection of VRFs to HR 1 | bar: 2022-08-02
| #REF! | Startup RTUs 1,2,3,4 & CME 1 & 2 | bar: 2022-08-01 to 2022-08-04
| #REF! | AES
Complete panel DPC | bar: 2022-08-01 to 2022-08-02
| #REF! | Balance of above ceiling inspection | bar: 2022-08-01
Fixtures and trim RR set B | bar: 2022-08-02
| #REF! | Final inspection | bar: 2022-08-03
M-Tech
| #REF! | Set fixtures in restroom set B | bar: 2022-08-01
| #REF! | Replace water heater in room 112 | bar: 2022-08-02
Final inspection | bar: 2022-08-02
#REF! | bar: 2022-08-03
| #REF! | B&L
| #REF! | Install FRL in corridors | bar: 2022-08-01 to 2022-08-03
| #REF! | Install FRL wood & metal trim | bar: 2022-08-02 to 2022-08-06; 2022-08-08 to 2022-08-10
Install the balance of ceiling tile | bar: 2022-08-01 to 2022-08-02; 2022-08-08 to 2022-08-10
Medel Painting
| #REF! | Prep and 2nd coat100 wing corridor | bar: 2022-08-03 to 2022-08-04
| #REF! | Tape and float 1st coat RR set B | bar: 2022-08-04 to 2022-08-06
| #REF! | Final coat corridor walls | bar: 2022-08-03 to 2022-08-06
| #REF! | 2nd coat FRL wood trim | bar: 2022-08-04 to 2022-08-06; 2022-08-08 to 2022-08-13
Paramount Company & Flooring
| #REF! | Complete wall grout in RR set B | bar: 2022-08-01
| #REF! | VCT & rubber base Install 100 wing
#REF! | bar: 2022-08-03 to 2022-08-06
| #REF! | Convergence
| #REF! | reinstall devices | bar: 2022-08-01 to 2022-08-05
| #REF! | Texas Star
| #REF! | Reinstall devices | bar: 2022-08-01 to 2022-08-06
| #REF! | Ace Audio
| #REF! | Install clocks and speakers in corridors | bar: 2022-08-01 to 2022-08-06
#REF!
| #REF! | JLT
| #REF! | Install owner provided accessories in set A & C | bar: 2022-08-02
| #REF! | Install RR partitions and accessories in set B | bar: 2022-08-02
Cleaning
#REF!
| #REF! | Kitchen and cafateria | bar: 2022-08-03
Main corridprs and RR | bar: 2022-08-04 to 2022-08-06
| #REF! | Fire final | bar: 2022-08-04
| #REF! | Building final | bar: 2022-08-05
#REF!
#REF!

## 3 Week Look-Ahead Schedule
3 WEEK LOOK-AHEAD SCHEDULE
ENTER PROJECT NAME HERE
|  | X = scheduled |  |  |  | D = delayed |  |  |  | H = holiday
|  | ENTER DATE | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
SUBCONTRACTOR - TASK |  | M | T | W | Th | F | Sa | Su | M | T | W | TH | F | Sa | Su | M | T | W | Th | F | Sa | Su