## 2 Week Look-Ahead Schedule
New Tech
2 week
|  | 2022-11-30 | 2022-12-01 | 2022-12-02 | 2022-12-03 | 2022-12-04 | 2022-12-05 | 2022-12-06 | 2022-12-07 | 2022-12-08 | 2022-12-09 | 2022-12-10 | 2022-12-11 | 2022-12-12 | 2022-12-13 | 2022-12-14 | 2022-12-15 | 2022-12-16 | 2022-12-17 | 2022-12-04 | 2022-12-05 | 2022-12-06 | 2022-12-07 | 2022-12-08 | 2022-12-09 | 2022-12-10 | 2022-12-11 | 2022-12-12 | 2022-12-13 | 2022-12-14
SUBCONTRACTOR - TASK |  | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed
Utilities
| Install conduit for secondary power ( pending cost approva)l | Wed: Pending; Thu: Pending; Fri: Pending; Mon: Pending; Tue: Pending; Wed: Pending; Thu: Pending; Fri: Pending; Mon: Pending; Tue: Pending; Wed: Pending; Thu: Pending; Fri: Pending
| Fireline Pending underground permit approval | Wed: Pending; Thu: Pending; Fri: Pending; Sat: Pending; Sun: Pending; Mon: Pending; Tue: Pending; Wed: Pending; Thu: Pending; Fri: Pending; Sat: Pending; Sun: Pending; Mon: Pending; Tue: Pending; Wed: Pending; Thu: Pending; Fri: Pending
Concrete
Complete P-3 piers om grid 10 ( All piers completed) | bar: Wed to Thu
Excavate perimeter grade beams | bar: Fri; Mon to Thu
Recieve rebar and void forms for grade beams | bar: Thu to Fri
Install grade beam rebar and anchor bolts for columns | bar: Mon to Fri
Plumbing | bar: Mon to Sat; Mon to Wed
| Rough in domestic water and dry well ( pending #11 above) | Wed: Pending; Thu: Pending; Fri: Pending; Sat: Pending; Sun: Pending; Mon: Pending; Tue: Pending; Wed: Pending; Thu: Pending; Fri: Pending; Sat: Pending; Sun: Pending; Mon: Pending; Tue: Pending; Wed: Pending; Thu: Pending; Fri: Pending
Green is scheduled work
Pending

## 3 Week Look-Ahead Schedule
3 WEEK LOOK-AHEAD SCHEDULE
ENTER PROJECT NAME HERE
|  | X = scheduled |  |  |  | D = delayed |  |  |  | H = holiday
|  | ENTER DATE | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
SUBCONTRACTOR - TASK |  | M | T | W | Th | F | Sa | Su | M | T | W | TH | F | Sa | Su | M | T | W | Th | F | Sa | Su