## 2 Week Look-Ahead Schedule
2 WEEK LOOK-AHEAD SCHEDULE
MSHS Gym & MPB
|  | X = scheduled |  |  |  | D = delayed |  |  |  | H = holiday
|  | 2023-02-20 | 2023-02-21 | 2023-02-22 | 2023-02-23 | 2023-02-24 | 2023-02-25 | 2023-02-26 | 2023-02-27 | 2023-02-28 | 2023-03-01 | 2023-03-02 | 2023-03-03 | 2023-03-04 | 2023-03-05
SUBCONTRACTOR - TASK |  | M | T | W | Th | F | Sa | Su | M | T | W | TH | F | Sa | Su
Practice Gym
Drilling/casing/pouring piers at gym | bar: 2023-02-20 to 2023-02-24; 2023-02-27 to 2023-03-03
Pier and building corner lay out | bar: 2023-02-20 to 2023-02-24; 2023-02-27 to 2023-03-03
Tie rebar cages for piers | bar: 2023-02-22 to 2023-02-23; 2023-02-27 to 2023-03-03
Multi Purpose Building | bar: 2023-02-23 to 2023-02-24; 2023-02-27 to 2023-03-03
Drilling/casing/pouring piers at MPB | bar: 2023-02-20 to 2023-02-24; 2023-02-27 to 2023-03-03
Grade beam installation at MPB | bar: 2023-02-20 to 2023-02-24; 2023-02-27 to 2023-03-03
green is ongoing work
yellow is rain delayed

## 3 Week Look-Ahead Schedule
3 WEEK LOOK-AHEAD SCHEDULE
ENTER PROJECT NAME HERE
|  | X = scheduled |  |  |  | D = delayed |  |  |  | H = holiday
|  | ENTER DATE | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
SUBCONTRACTOR - TASK |  | M | T | W | Th | F | Sa | Su | M | T | W | TH | F | Sa | Su | M | T | W | Th | F | Sa | Su