## 2 Week Look-Ahead Schedule
2 WEEK LOOK-AHEAD SCHEDULE
ENTER PROJECT NAME HERE
|  | X = scheduled |  |  |  | D = delayed |  |  |  | H = holiday
|  | ENTER DATE | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
SUBCONTRACTOR - TASK |  | M | T | W | Th | F | Sa | Su | M | T | W | TH | F | Sa | Su

## 3 Week Look-Ahead Schedule
3 WEEK LOOK-AHEAD SCHEDULE
TCESD 2 STATION 6
|  | X = scheduled |  |  |  | D = delayed |  |  |  | H = holiday
|  | 2023-01-02 | 2023-01-03 | 2023-01-04 | 2023-01-05 | 2023-01-06 | 2023-01-07 | 2023-01-08 | 2023-01-09 | 2023-01-10 | 2023-01-11 | 2023-01-12 | 2023-01-13 | 2023-01-14 | 2023-01-15 | 2023-01-16 | 2023-01-17 | 2023-01-18 | 2023-01-19 | 2023-01-20 | 2023-01-21 | 2023-01-22
SUBCONTRACTOR - TASK |  | M | T | W | Th | F | Sa | Su | M | T | W | TH | F | Sa | Su | M | T | W | Th | F | Sa | Su
Centex Masonry CMU Walls | bar: 2023-01-02 to 2023-01-06; 2023-01-09 to 2023-01-13; 2023-01-16 to 2023-01-20
B&L Metal Stud Framing | bar: 2023-01-02 to 2023-01-06; 2023-01-09 to 2023-01-13; 2023-01-16 to 2023-01-20; 2023-01-22
BJ Electric CMU Wall Rough In | bar: 2023-01-05 to 2023-01-06; 2023-01-09 to 2023-01-13; 2023-01-16 to 2023-01-20
Wolff Concrete Retaining Wall |  | 2023-01-02: H; 2023-01-03: D; 2023-01-04: D; 2023-01-05: D; 2023-01-06: X; 2023-01-09: X; 2023-01-10: X; 2023-01-11: X; 2023-01-12: X; 2023-01-13: X
Wolff Concrete at Entrance & Exit to AB | bar: 2023-01-09 to 2023-01-13
CMP Structural Steel | bar: 2023-01-06; 2023-01-09 to 2023-01-13; 2023-01-16 to 2023-01-17
CMP Structural AB Decking | bar: 2023-01-09 to 2023-01-12
Red & White Greenery Sleeves at Drives | bar: 2023-01-18 to 2023-01-20
Kinney Plumbing CMU Rough In | bar: 2023-01-04 to 2023-01-06; 2023-01-09 to 2023-01-13; 2023-01-16 to 2023-01-20
PARKING & DRIVE PAVING DATES
Champion Paving Prep | bar: 2023-01-18 to 2023-01-20
Champion Lime Stabilization |  | 2023-01-20: 2023-01-23
Wolff Concrete Paving |  | 2023-01-20: 2023-01-26