## 2 Week Look-Ahead Schedule
2 WEEK LOOK-AHEAD SCHEDULE
ENTER PROJECT NAME HERE
|  | X = scheduled |  |  |  | D = delayed |  |  |  | H = holiday
|  | ENTER DATE | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
SUBCONTRACTOR - TASK |  | M | T | W | Th | F | Sa | Su | M | T | W | TH | F | Sa | Su

## 3 Week Look-Ahead Schedule
3 WEEK LOOK-AHEAD SCHEDULE
TCESD 2 STATION 6
|  | X = scheduled |  |  |  | D = delayed |  |  |  | H = holiday
|  | 2023-02-27 | 2023-02-28 | 2023-03-01 | 2023-03-02 | 2023-03-03 | 2023-03-04 | 2023-03-05 | 2023-03-06 | 2023-03-07 | 2023-03-08 | 2023-03-09 | 2023-03-10 | 2023-03-11 | 2023-03-12 | 2023-03-13 | 2023-03-14 | 2023-03-15 | 2023-03-16 | 2023-03-17 | 2023-03-18 | 2023-03-19
SUBCONTRACTOR - TASK |  | M | T | W | Th | F | Sa | Su | M | T | W | TH | F | Sa | Su | M | T | W | Th | F | Sa | Su
Centex Masonry CMU Walls | bar: 2023-02-27 to 2023-03-03; 2023-03-06 to 2023-03-10; 2023-03-13 to 2023-03-17
B&L Metal Stud Framing | bar: 2023-02-27 to 2023-03-03; 2023-03-06 to 2023-03-10; 2023-03-13 to 2023-03-17; 2023-03-19
BJ Electric CMU & LQ Wall Rough In | bar: 2023-02-27 to 2023-03-03; 2023-03-06 to 2023-03-10; 2023-03-13 to 2023-03-14
B&L Set Trusses LQ | bar: 2023-02-27 to 2023-03-03; 2023-03-06 to 2023-03-10; 2023-03-13 to 2023-03-17
CMP Structural Steel | bar: 2023-03-01 to 2023-03-03; 2023-03-06
Kinney Plumbing CMU & LQ Rough In | bar: 2023-02-28; 2023-03-06 to 2023-03-10; 2023-03-13 to 2023-03-17
B&L Exterior Sheathing | bar: 2023-02-27 to 2023-03-03; 2023-03-06 to 2023-03-10; 2023-03-13 to 2023-03-17
Wolff Concrete Slab Pour Backs & Grout | bar: 2023-03-07 to 2023-03-08
B&L Wood Blocking at AB Roof | bar: 2023-02-27 to 2023-03-01
PARKING & DRIVE PAVING DATES
Wolff Concrete Wreck Forms & Clean Up | bar: 2023-03-06 to 2023-03-08
Wolff Concrete Paving 3rd Pour | bar: 2023-03-01