## 2 Week Look-Ahead Schedule
2 WEEK LOOK-AHEAD SCHEDULE
ENTER PROJECT NAME HERE
|  | X = scheduled |  |  |  | D = delayed |  |  |  | H = holiday
|  | ENTER DATE | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
SUBCONTRACTOR - TASK |  | M | T | W | Th | F | Sa | Su | M | T | W | TH | F | Sa | Su

## 3 Week Look-Ahead Schedule
3 WEEK LOOK-AHEAD SCHEDULE
TCESD 2 STATION 6
|  | X = scheduled |  |  |  | D = delayed |  |  |  | H = holiday
|  | 2022-12-26 | 2022-12-27 | 2022-12-28 | 2022-12-29 | 2022-12-30 | 2022-12-31 | 2023-01-01 | 2023-01-02 | 2023-01-03 | 2023-01-04 | 2023-01-05 | 2023-01-06 | 2023-01-07 | 2023-01-08 | 2023-01-09 | 2023-01-10 | 2023-01-11 | 2023-01-12 | 2023-01-13 | 2023-01-14 | 2023-01-15
SUBCONTRACTOR - TASK |  | M | T | W | Th | F | Sa | Su | M | T | W | TH | F | Sa | Su | M | T | W | Th | F | Sa | Su
Centex Masonry CMU Walls | bar: 2022-12-26 to 2022-12-30; 2023-01-02 to 2023-01-06; 2023-01-09 to 2023-01-13
B&L Metal Stud Framing | bar: 2022-12-26 to 2022-12-30; 2023-01-02 to 2023-01-06; 2023-01-09 to 2023-01-13; 2023-01-15
BJ Electric CMU Wall Rough In | bar: 2022-12-29 to 2022-12-30; 2023-01-02 to 2023-01-06; 2023-01-09 to 2023-01-13
Wolff Concrete Retaining Wall |  | H | D | D | D | D |  |  | H | D | D | D | D |  |  | X | X | X | X | X
Wolff Concrete at Entrance & Exit to AB | bar: 2023-01-02 to 2023-01-06
CE Roof Storm Drain & French Drain | bar: 2022-12-26 to 2022-12-29
CMP Structural Steel | bar: 2023-01-09 to 2023-01-13
Red & White Greenery Sleeves at Drives | bar: 2023-01-11 to 2023-01-13
Wolff Concrete Drill & Pour Light Poles | bar: 2023-01-11 to 2023-01-13
BJ Light Pole Electrical Conduits | bar: 2022-12-26 to 2022-12-27
Element 7 Floors AB | bar: 2022-12-30