## 2 Week Look-Ahead Schedule
2 WEEK LOOK-AHEAD SCHEDULE
ENTER PROJECT NAME HERE
|  | X = scheduled |  |  |  | D = delayed |  |  |  | H = holiday
|  | ENTER DATE | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
SUBCONTRACTOR - TASK |  | M | T | W | Th | F | Sa | Su | M | T | W | TH | F | Sa | Su

## 3 Week Look-Ahead Schedule
3 WEEK LOOK-AHEAD SCHEDULE
TCESD 2 STATION 6
|  | X = scheduled |  |  |  | D = delayed |  |  |  | H = holiday
|  | 2022-08-15 | 2022-08-16 | 2022-08-17 | 2022-08-18 | 2022-08-19 | 2022-08-20 | 2022-08-21 | 2022-08-22 | 2022-08-23 | 2022-08-24 | 2022-08-25 | 2022-08-26 | 2022-08-27 | 2022-08-28 | 2022-08-29 | 2022-08-30 | 2022-08-31 | 2022-09-01 | 2022-09-02 | 2022-09-03 | 2022-09-04
SUBCONTRACTOR - TASK |  | M | T | W | Th | F | Sa | Su | M | T | W | TH | F | Sa | Su | M | T | W | Th | F | Sa | Su
Wolff Concrete Grade Beam Excavation | bar: 2022-08-15 to 2022-08-19; 2022-08-22 to 2022-08-27; 2022-08-29 to 2022-08-30
Wolff Concrete Grade Beam Forms | bar: 2022-08-15 to 2022-08-19; 2022-08-22 to 2022-08-27; 2022-08-29 to 2022-09-03
Wolff Concrete Grade Reinforcing Steel | bar: 2022-08-20; 2022-08-22 to 2022-08-27; 2022-08-29 to 2022-09-03
Wolff Concrete 1st Grade Beam Pour LQ | bar: 2022-08-30 to 2022-08-31
CE Subdivision Wastewater Line | bar: 2022-08-15 to 2022-08-20; 2022-08-22 to 2022-08-27; 2022-08-29 to 2022-09-03
BJ Electric Underslab Rough
Kinneys Plumbing Underslab Rough