## 2 Week Look-Ahead Schedule
2 WEEK LOOK-AHEAD SCHEDULE
ENTER PROJECT NAME HERE
|  | X = scheduled |  |  |  | D = delayed |  |  |  | H = holiday
|  | ENTER DATE | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE! | #VALUE!
SUBCONTRACTOR - TASK |  | M | T | W | Th | F | Sa | Su | M | T | W | TH | F | Sa | Su

## 3 Week Look-Ahead Schedule
3 WEEK LOOK-AHEAD SCHEDULE
TCESD 2 STATION 6
|  | X = scheduled |  |  |  | D = delayed |  |  |  | H = holiday
|  | 2023-01-23 | 2023-01-24 | 2023-01-25 | 2023-01-26 | 2023-01-27 | 2023-01-28 | 2023-01-29 | 2023-01-30 | 2023-01-31 | 2023-02-01 | 2023-02-02 | 2023-02-03 | 2023-02-04 | 2023-02-05 | 2023-02-06 | 2023-02-07 | 2023-02-08 | 2023-02-09 | 2023-02-10 | 2023-02-11 | 2023-02-12
SUBCONTRACTOR - TASK |  | M | T | W | Th | F | Sa | Su | M | T | W | TH | F | Sa | Su | M | T | W | Th | F | Sa | Su
Centex Masonry CMU Walls | bar: 2023-01-23 to 2023-01-27; 2023-01-30 to 2023-02-03; 2023-02-06 to 2023-02-10
B&L Metal Stud Framing | bar: 2023-01-23 to 2023-01-27; 2023-01-30 to 2023-02-03; 2023-02-06 to 2023-02-10; 2023-02-12
BJ Electric CMU Wall Rough In | bar: 2023-01-23 to 2023-01-27; 2023-01-30 to 2023-02-03; 2023-02-06 to 2023-02-10
B&L Set Trusses LQ | bar: 2023-01-26 to 2023-01-27; 2023-01-30 to 2023-02-03; 2023-02-06
CMP Structural Steel | bar: 2023-02-06 to 2023-02-09
Champion Saw Cut Approaches | bar: 2023-01-27
B&L Exterior Sheathing | bar: 2023-01-23 to 2023-01-27; 2023-01-30 to 2023-02-03
Red & White Greenery Sleeves at Drives | bar: 2023-02-10
Kinney Plumbing CMU Rough In | bar: 2023-01-23 to 2023-01-27; 2023-01-30 to 2023-02-03; 2023-02-06 to 2023-02-10
PARKING & DRIVE PAVING DATES
Champion Paving Prep | bar: 2023-01-26 to 2023-01-28; 2023-01-30; 2023-02-06 to 2023-02-10
Champion Lime Stabilization | bar: 2023-01-30; 2023-02-06
Wolff Concrete Paving Forms | bar: 2023-02-03 to 2023-02-04; 2023-02-06 to 2023-02-10
Wolff Concrete Paving 1st Pour | bar: 2023-02-07
Wolff Concrete Paving 2nd Pour
Wolff Concrete Approaches