## 2 Week Look-Ahead Schedule
2 WEEK LOOK-AHEAD SCHEDULE
TCESD 2 STATION 6
|  | X = scheduled |  |  |  | D = delayed |  |  |  | H = holiday
|  | 2022-06-27 | 2022-06-28 | 2022-06-29 | 2022-06-30 | 2022-07-01 | 2022-07-02 | 2022-07-03 | 2022-07-04 | 2022-07-05 | 2022-07-06 | 2022-07-07 | 2022-07-08 | 2022-07-09 | 2022-07-10
SUBCONTRACTOR - TASK |  | M | T | W | Th | F | Sa | Su | M | T | W | TH | F | Sa | Su
Champion Site Prep | bar: 2022-06-27 to 2022-07-02; 2022-07-04
Eagle Eye Survey | bar: 2022-07-01; 2022-07-04
CE Detention Outfall | bar: 2022-07-04 to 2022-07-09
Wolff Concrete Piers | bar: 2022-07-04 to 2022-07-09
Wolff Concrete Gradebeams & Rebar
Kinneys Plumbing Underslab Rough
BJ Electric Underslab Rough
CE On Site Utilities
CE 4" Waste Line

## 3 Week Look-Ahead Schedule
3 WEEK LOOK-AHEAD SCHEDULE
TCESD 2 STATION 6 | [18 empty] | \\Bra-dc01\data\Company Shared Folders\Operations\Current Jobs\012211 TCESD #2 - Fire Station 6\Operations\Schedules\2-Week Look Ahead Schedules\2_3-Week-Look-Ahead-TCESD 2 #6.xlsx
|  | X = scheduled |  |  |  | D = delayed |  |  |  | H = holiday
|  | 2022-07-11 | 2022-07-12 | 2022-07-13 | 2022-07-14 | 2022-07-15 | 2022-07-16 | 2022-07-17 | 2022-07-18 | 2022-07-19 | 2022-07-20 | 2022-07-21 | 2022-07-22 | 2022-07-23 | 2022-07-24 | 2022-07-25 | 2022-07-26 | 2022-07-27 | 2022-07-28 | 2022-07-29 | 2022-07-30 | 2022-07-31
SUBCONTRACTOR - TASK |  | M | T | W | Th | F | Sa | Su | M | T | W | TH | F | Sa | Su | M | T | W | Th | F | Sa | Su
CE Detention Outfall / Site Storm Utilities | bar: 2022-07-11 to 2022-07-15; 2022-07-18 to 2022-07-23; 2022-07-25 to 2022-07-26
CE Waste Water Line | bar: 2022-07-20 to 2022-07-23; 2022-07-25 to 2022-07-30
Wolff Concrete Piers | bar: 2022-07-11 to 2022-07-15; 2022-07-18 to 2022-07-23; 2022-07-25 to 2022-07-30
Wolff Concrete Grade Beams
Building Permit / Critical Path | bar: 2022-07-11 to 2022-07-15
Kinneys Plumbing Underslab Rough
BJ Electric Underslab Rough