## 2 Week Look-Ahead Schedule
2 WEEK LOOK-AHEAD SCHEDULE
TCESD 2 STATION 6
|  | X = scheduled |  |  |  | D = delayed |  |  |  | H = holiday
|  | 2022-06-27 | 2022-06-28 | 2022-06-29 | 2022-06-30 | 2022-07-01 | 2022-07-02 | 2022-07-03 | 2022-07-04 | 2022-07-05 | 2022-07-06 | 2022-07-07 | 2022-07-08 | 2022-07-09 | 2022-07-10
SUBCONTRACTOR - TASK |  | M | T | W | Th | F | Sa | Su | M | T | W | TH | F | Sa | Su
Champion Site Prep | bar: 2022-06-27 to 2022-07-02; 2022-07-04
Eagle Eye Survey | bar: 2022-07-01; 2022-07-04
CE Detention Outfall | bar: 2022-07-04 to 2022-07-09
Wolff Concrete Piers | bar: 2022-07-04 to 2022-07-09
Wolff Concrete Gradebeams & Rebar
Kinneys Plumbing Underslab Rough
BJ Electric Underslab Rough
CE On Site Utilities
CE 4" Waste Line

## 3 Week Look-Ahead Schedule
3 WEEK LOOK-AHEAD SCHEDULE
TCESD 2 STATION 6
|  | X = scheduled |  |  |  | D = delayed |  |  |  | H = holiday
|  | 2022-06-27 | 2022-06-28 | 2022-06-29 | 2022-06-30 | 2022-07-01 | 2022-07-02 | 2022-07-03 | 2022-07-04 | 2022-07-05 | 2022-07-06 | 2022-07-07 | 2022-07-08 | 2022-07-09 | 2022-07-10 | 2022-07-11 | 2022-07-12 | 2022-07-13 | 2022-07-14 | 2022-07-15 | 2022-07-16 | 2022-07-17
SUBCONTRACTOR - TASK |  | M | T | W | Th | F | Sa | Su | M | T | W | TH | F | Sa | Su | M | T | W | Th | F | Sa | Su
Champion Site Prep | bar: 2022-06-27 to 2022-07-01
Eagle Eye Survey | bar: 2022-07-01
CE Detention Outfall / Site Utilities | bar: 2022-07-04 to 2022-07-09; 2022-07-11 to 2022-07-16
Wolff Concrete Piers | bar: 2022-07-04 to 2022-07-09; 2022-07-11 to 2022-07-16
Wolff Concrete Grade Beams | bar: 2022-07-13 to 2022-07-16
Building Permit / Critical Path | bar: 2022-07-05
Kinneys Plumbing Underslab Rough
BJ Electric Underslab Rough