## Sheet1
WD = Weather Delay
[12 empty] | Active on schedule |  |  | weekend
[12 empty] | Inactive on schedule |  | X= Scheduled
[11 empty] | cont. =continued to next week |  |  | D= delayed
2017-07-28
2017-07-29
2017-07-30
2017-07-31
2017-08-01
2017-08-02
2017-08-03
Region 13 La Grange |  | Date | 2022-01-12 | [7 empty] | (X) = Possible Scheduled Day |  |  |  | Holiday
2 Week Look Ahead | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday
Item | 2022-01-12 | 2022-01-13 | 2022-01-14 | 2022-01-15 | 2022-01-16 | 2022-01-17 | 2022-01-18 | 2022-01-19 | 2022-01-20 | 2022-01-21 | 2022-01-22 | 2022-01-23 | 2022-01-24 | 2022-01-25 | 2022-01-26 | 2022-01-27 | 2022-01-28
Braun & Butler
-OAC pre con | bar: 2022-01-16
-slab x-ray | bar: 2022-01-23
-existing slab repair
-mobilize onsite | bar: 2022-01-12 to 2022-01-13
-make safe | bar: 2022-01-12 to 2022-01-13
Duvall
-electrical makesafe | bar: 2022-01-12 to 2022-01-13
-demo existing ceiling light fixtures | bar: 2022-01-12 to 2022-01-13; 2022-01-16 to 2022-01-20
-install temp lighting | bar: 2022-01-12 to 2022-01-13
-electrical demo | bar: 2022-01-16 to 2022-01-20; 2022-01-23 to 2022-01-27
-FA make safe/demo | bar: 2022-01-12 to 2022-01-13; 2022-01-16 to 2022-01-18
-Area A rough in
Aircraft
-make safe air (cover returns) | bar: 2022-01-12 to 2022-01-13
-demo HVAC | bar: 2022-01-12 to 2022-01-13
-demo RTU
-HVAC rough |  |  |  |  | X | X | X | X | X |  |  | X | X | X | X | X | cont
Plumbers
-demo wet wall plumbing | 2022-01-14: PENDING
-underground sawcut layout
ARC
-floor demo | bar: 2022-01-12
-demo ceiling grid | bar: 2022-01-13; 2022-01-16 to 2022-01-18
-demo walls | bar: 2022-01-12 to 2022-01-13; 2022-01-16
B&L
-demo north wall for openings | bar: 2022-01-19 to 2022-01-20
-wall layout area A | bar: 2022-01-20; 2022-01-23 to 2022-01-24
-framing Area A | 2022-01-24: X; 2022-01-25: X; 2022-01-26: X; 2022-01-27: X; 2022-01-28: cont.
Steel
Meetings/Inspections