## Sheet1
WD = Weather Delay
[12 empty] | Active on schedule |  |  | weekend
[12 empty] | Inactive on schedule |  | X= Scheduled
[11 empty] | cont. =continued to next week |  |  | D= delayed
2017-07-28
2017-07-29
2017-07-30
2017-07-31
2017-08-01
2017-08-02
2017-08-03
Reghion 13 La Grange |  | Date | 2023-03-01 | [7 empty] | (X) = Possible Scheduled Day |  |  |  | Holiday
6 Week Look Ahead | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday
Item | time axis 2023-03-02 to 2023-04-15
Braun & Butler
-Floor/final paint/casework meeting | bar: 2023-03-02 to 2023-03-03; 2023-03-06 to 2023-03-10; 2023-03-13 to 2023-03-17; 2023-03-20 to 2023-03-24; 2023-03-27 to 2023-03-31; 2023-04-03 to 2023-04-07; 2023-04-10 to 2023-04-14
-roof repair | 2023-03-04: ASAP
-assess HVAC | bar: 2023-03-02 to 2023-03-03; 2023-03-06 to 2023-03-10; 2023-03-13 to 2023-03-17; 2023-03-20 to 2023-03-24; 2023-03-27 to 2023-03-31; 2023-04-03 to 2023-04-07; 2023-04-10 to 2023-04-14
-plumbing pour back | bar: 2023-03-02
-steel delivered to site | 2023-03-04: PENDING; 2023-03-13: X; 2023-03-14: X; 2023-03-15: X; 2023-03-16: X; 2023-03-17: X
-cut cmu and mezzanine for FCU 100 | bar: 2023-03-07 to 2023-03-09
-doors and hardware onsite | 2023-03-04: MAY
-doorframes onsite | bar: 2023-03-02 to 2023-03-03; 2023-03-06 to 2023-03-10; 2023-03-13 to 2023-03-17; 2023-03-20 to 2023-03-24; 2023-03-27 to 2023-03-31; 2023-04-03 to 2023-04-07; 2023-04-10 to 2023-04-14
Duvall
-above ceiling rough area A | bar: 2023-03-02 to 2023-03-03
-pull wire area B | bar: 2023-03-02 to 2023-03-03; 2023-03-06 to 2023-03-10; 2023-03-13 to 2023-03-17; 2023-03-20 to 2023-03-24; 2023-03-27 to 2023-03-31; 2023-04-03 to 2023-04-07; 2023-04-10 to 2023-04-14
-pull wire area C | bar: 2023-03-02 to 2023-03-03; 2023-03-06 to 2023-03-10
-above ceiling inspection | bar: 2023-03-02 to 2023-03-03; 2023-03-06 to 2023-03-10; 2023-03-13 to 2023-03-17; 2023-03-20 to 2023-03-24; 2023-03-27 to 2023-03-31; 2023-04-03 to 2023-04-07; 2023-04-10 to 2023-04-14
-pullwire area A | bar: 2023-03-16 to 2023-03-17; 2023-03-20 to 2023-03-21
-energize | bar: 2023-03-02 to 2023-03-03; 2023-03-06 to 2023-03-10; 2023-03-13 to 2023-03-17; 2023-03-20 to 2023-03-24; 2023-03-27 to 2023-03-31; 2023-04-03 to 2023-04-07; 2023-04-10 to 2023-04-14
-in wall rough area A | bar: 2023-03-02 to 2023-03-03; 2023-03-06 to 2023-03-10; 2023-03-13 to 2023-03-17; 2023-03-20 to 2023-03-24; 2023-03-27 to 2023-03-31; 2023-04-03 to 2023-04-07; 2023-04-10 to 2023-04-14
-in wall inspection | bar: 2023-03-08
-power to roof mechincal units | bar: 2023-03-02 to 2023-03-03; 2023-03-06 to 2023-03-10; 2023-03-13 to 2023-03-17; 2023-03-20 to 2023-03-24; 2023-03-27 to 2023-03-31; 2023-04-03 to 2023-04-07; 2023-04-10 to 2023-04-14
-exterior lighting | bar: 2023-03-27 to 2023-03-31
-ceiling rough in | bar: 2023-03-02 to 2023-03-03; 2023-03-06 to 2023-03-10; 2023-03-13 to 2023-03-17; 2023-03-20 to 2023-03-24; 2023-03-27 to 2023-03-31; 2023-04-03 to 2023-04-07; 2023-04-10 to 2023-04-14
-FA back box rough in | 2023-03-02: X; 2023-03-03: X; 2023-03-04: ASAP
-ceiling trim out area B | bar: 2023-03-27 to 2023-03-31
-ceiling trim out area C | bar: 2023-03-02 to 2023-03-03; 2023-03-06 to 2023-03-10; 2023-03-13 to 2023-03-17; 2023-03-20 to 2023-03-24; 2023-03-27 to 2023-03-31; 2023-04-03 to 2023-04-07; 2023-04-10 to 2023-04-14
-ceiling trim out area a | bar: 2023-03-27 to 2023-03-31
Aircraft
-above ceiling rough area C | bar: 2023-03-02 to 2023-03-03; 2023-03-06 to 2023-03-10; 2023-03-13 to 2023-03-17; 2023-03-20 to 2023-03-24; 2023-03-27 to 2023-03-31; 2023-04-03 to 2023-04-07; 2023-04-10 to 2023-04-14
-above ceiling rough area B | bar: 2023-03-02 to 2023-03-03; 2023-03-06 to 2023-03-07
-above ceiling rough area A | bar: 2023-03-02 to 2023-03-03; 2023-03-06 to 2023-03-10; 2023-03-13 to 2023-03-17; 2023-03-20 to 2023-03-24; 2023-03-27 to 2023-03-31; 2023-04-03 to 2023-04-07; 2023-04-10 to 2023-04-14
-above ceiling inspection | bar: 2023-03-03; 2023-03-22
-insulate | bar: 2023-03-02 to 2023-03-03; 2023-03-06 to 2023-03-10; 2023-03-13 to 2023-03-17; 2023-03-20 to 2023-03-24; 2023-03-27 to 2023-03-31; 2023-04-03 to 2023-04-07; 2023-04-10 to 2023-04-14
-roof work | bar: 2023-03-15 to 2023-03-17; 2023-03-20 to 2023-03-24
-HVAC Startup | bar: 2023-03-02 to 2023-03-03; 2023-03-06 to 2023-03-10; 2023-03-13 to 2023-03-17; 2023-03-20 to 2023-03-24; 2023-03-27 to 2023-03-31; 2023-04-03 to 2023-04-07; 2023-04-10 to 2023-04-14
-grille out ceilings corridors Area B | bar: 2023-03-13 to 2023-03-17; 2023-03-20 to 2023-03-24; 2023-03-27 to 2023-03-31
-grille out ceilings corridors Area C | bar: 2023-03-02 to 2023-03-03; 2023-03-06 to 2023-03-10; 2023-03-13 to 2023-03-17; 2023-03-20 to 2023-03-24; 2023-03-27 to 2023-03-31; 2023-04-03 to 2023-04-07; 2023-04-10 to 2023-04-14
-ceiling layout Classrooms | bar: 2023-03-13 to 2023-03-17
-ceiling layout offices | bar: 2023-03-02 to 2023-03-03; 2023-03-06 to 2023-03-10; 2023-03-13 to 2023-03-17; 2023-03-20 to 2023-03-24; 2023-03-27 to 2023-03-31; 2023-04-03 to 2023-04-07; 2023-04-10 to 2023-04-14
-grille out area A | bar: 2023-03-27 to 2023-03-31
Holmans
-plumbing demo | bar: 2023-03-02 to 2023-03-03; 2023-03-06 to 2023-03-10; 2023-03-13 to 2023-03-17
-above ceiling rough | bar: 2023-03-02 to 2023-03-03; 2023-03-06 to 2023-03-10; 2023-03-13 to 2023-03-17; 2023-03-20 to 2023-03-24; 2023-03-27 to 2023-03-31; 2023-04-03 to 2023-04-07; 2023-04-10 to 2023-04-14
-restroom rough in | bar: 2023-03-02 to 2023-03-03; 2023-03-06 to 2023-03-10
-above ceiling inspection | bar: 2023-03-02 to 2023-03-03; 2023-03-06 to 2023-03-10; 2023-03-13 to 2023-03-17; 2023-03-20 to 2023-03-24; 2023-03-27 to 2023-03-31; 2023-04-03 to 2023-04-07; 2023-04-10 to 2023-04-14
-in wall inspection | bar: 2023-03-02; 2023-03-06 to 2023-03-10
-set out | 2023-03-27: X; 2023-03-28: X; 2023-03-29: X; 2023-03-30: X; 2023-03-31: X; 2023-04-10: (X); 2023-04-11: (X); 2023-04-12: (X); 2023-04-13: (X); 2023-04-14: (X)
ARC
-chemical removal | 2023-03-04: ASAP
B&L
-ceiling grid Area C | bar: 2023-03-02 to 2023-03-03; 2023-03-06 to 2023-03-10; 2023-03-13 to 2023-03-17; 2023-03-20 to 2023-03-24; 2023-03-27 to 2023-03-31; 2023-04-03 to 2023-04-07; 2023-04-10 to 2023-04-14
-ceiling grid area B | bar: 2023-03-06 to 2023-03-10; 2023-03-13 to 2023-03-17
-Frame area A | bar: 2023-03-02 to 2023-03-03; 2023-03-06 to 2023-03-10; 2023-03-13 to 2023-03-17; 2023-03-20 to 2023-03-24; 2023-03-27 to 2023-03-31; 2023-04-03 to 2023-04-07; 2023-04-10 to 2023-04-14
-frame corridor ceilings | bar: 2023-03-02 to 2023-03-03
-sheetrock corridor ceilings | bar: 2023-03-02 to 2023-03-03; 2023-03-06 to 2023-03-10; 2023-03-13 to 2023-03-17; 2023-03-20 to 2023-03-24; 2023-03-27 to 2023-03-31; 2023-04-03 to 2023-04-07; 2023-04-10 to 2023-04-14
-furrdowns for steel beams | 2023-03-04: PENDING; 2023-03-05: STEEL
-insulate and two side area A | bar: 2023-03-09 to 2023-03-10; 2023-03-13 to 2023-03-14
-drop ceiling tile | bar: 2023-03-20 to 2023-03-24
-doors and hardware | 2023-03-04: MAY
-one side area A | bar: 2023-03-02 to 2023-03-03; 2023-03-06 to 2023-03-10; 2023-03-13 to 2023-03-17; 2023-03-20 to 2023-03-24; 2023-03-27 to 2023-03-31; 2023-04-03 to 2023-04-07; 2023-04-10 to 2023-04-14
Fast Track
-unload steel | 2023-03-02: D; 2023-03-03: D; 2023-03-04: TBD; 2023-03-05: GC to confirm; 2023-03-06: D; 2023-03-07: D; 2023-03-08: D; 2023-03-09: D; 2023-03-10: D; 2023-03-13: (X)
-erect columns and beams | 2023-03-13: (X); 2023-03-14: X; 2023-03-15: X; 2023-03-16: X; 2023-03-17: X
Paramount
-floor prep/float | bar: 2023-04-03 to 2023-04-05
-ceramic tile in restrooms | bar: 2023-03-02 to 2023-03-03; 2023-03-06 to 2023-03-10; 2023-03-13 to 2023-03-17; 2023-03-20 to 2023-03-24; 2023-03-27 to 2023-03-31; 2023-04-03 to 2023-04-07; 2023-04-10 to 2023-04-14
-Flooring area A | 2023-04-15: cont.
-flooring area B | 2023-04-12: X; 2023-04-13: X; 2023-04-14: X; 2023-04-15: cont.
-flooring area C | bar: 2023-04-06 to 2023-04-07; 2023-04-10 to 2023-04-12
-wall base C | bar: 2023-03-02 to 2023-03-03; 2023-03-06 to 2023-03-10; 2023-03-13 to 2023-03-17; 2023-03-20 to 2023-03-24; 2023-03-27 to 2023-03-31; 2023-04-03 to 2023-04-07; 2023-04-10 to 2023-04-14
-wall base B/A
JLT Ginther
-install Tas | bar: 2023-04-03 to 2023-04-07; 2023-04-10 to 2023-04-14
Rob Pelletier
-field measure | 2023-03-04: PENDING; 2023-03-05: STEEL; 2023-03-12: D; 2023-03-19: D; 2023-03-20: (X)
-overhead track install | 2023-03-04: PENDING; 2023-03-05: STEEL; 2023-03-19: D; 2023-03-26: D; 2023-03-27: X; 2023-03-28: X; 2023-03-29: X; 2023-03-30: X; 2023-03-31: X
A1 Concrete
-sawcut for HVAC | bar: 2023-03-07 to 2023-03-09
Medel
-tape and float walls area B | bar: 2023-03-02 to 2023-03-03; 2023-03-06 to 2023-03-10
-first coat walls area B | bar: 2023-03-02 to 2023-03-03; 2023-03-06 to 2023-03-10; 2023-03-13 to 2023-03-17; 2023-03-20 to 2023-03-24; 2023-03-27 to 2023-03-31; 2023-04-03 to 2023-04-07; 2023-04-10 to 2023-04-14
-tape and float corridors Area B | bar: 2023-03-14 to 2023-03-17; 2023-03-20 to 2023-03-22
-first coat paint corridors area B | bar: 2023-03-02 to 2023-03-03; 2023-03-06 to 2023-03-10; 2023-03-13 to 2023-03-17; 2023-03-20 to 2023-03-24; 2023-03-27 to 2023-03-31; 2023-04-03 to 2023-04-07; 2023-04-10 to 2023-04-14
-tape and float area A | bar: 2023-03-13 to 2023-03-15; 2023-03-20 to 2023-03-23
-first coat paint area A | bar: 2023-03-02 to 2023-03-03; 2023-03-06 to 2023-03-10; 2023-03-13 to 2023-03-17; 2023-03-20 to 2023-03-24; 2023-03-27 to 2023-03-31; 2023-04-03 to 2023-04-07; 2023-04-10 to 2023-04-14
-final coat Area C | bar: 2023-04-10 to 2023-04-14
-final coat area B | 2023-04-15: cont.
CE
-excavate for utility line | bar: 2023-03-02 to 2023-03-03
-lay pipe | bar: 2023-03-02 to 2023-03-03; 2023-03-06 to 2023-03-10; 2023-03-13 to 2023-03-17; 2023-03-20 to 2023-03-24; 2023-03-27 to 2023-03-31; 2023-04-03 to 2023-04-07; 2023-04-10 to 2023-04-14
-inspection | bar: 2023-03-08
-backfill | bar: 2023-03-02 to 2023-03-03; 2023-03-06 to 2023-03-10; 2023-03-13 to 2023-03-17; 2023-03-20 to 2023-03-24; 2023-03-27 to 2023-03-31; 2023-04-03 to 2023-04-07; 2023-04-10 to 2023-04-14
-asphalt | bar: 2023-03-13 to 2023-03-14
Capitol
-firealarm rough in | 2023-03-02: X; 2023-03-03: X; 2023-03-04: PENDING; 2023-03-05: APPROVAL
-install FACP/annunciater | bar: 2023-03-02 to 2023-03-03; 2023-03-06 to 2023-03-10; 2023-03-13 to 2023-03-17; 2023-03-20 to 2023-03-24; 2023-03-27 to 2023-03-31; 2023-04-03 to 2023-04-07; 2023-04-10 to 2023-04-14
-trim out devices | bar: 2023-03-27 to 2023-03-31
Arcase
-install millwork | 2023-03-27: X; 2023-03-28: X; 2023-03-29: X; 2023-03-30: X; 2023-03-31: X; 2023-04-15: cont.
Exterior Sealant
Mascon
-roofing repair | 2023-03-04: ASAP; 2023-03-13: X; 2023-03-14: X; 2023-03-15: X; 2023-03-16: X; 2023-03-17: X; 2023-03-27: NLT
-VTR, Curbs, T-tops | bar: 2023-03-08 to 2023-03-10; 2023-03-13 to 2023-03-15
Building signage
Meetings/Inspections
-OAC | bar: 2023-03-06; 2023-03-13; 2023-03-20; 2023-03-27; 2023-04-03; 2023-04-10
-foreman meeting | bar: 2023-03-02 to 2023-03-03; 2023-03-06 to 2023-03-10; 2023-03-13 to 2023-03-17; 2023-03-20 to 2023-03-24; 2023-03-27 to 2023-03-31; 2023-04-03 to 2023-04-07; 2023-04-10 to 2023-04-14
-safety meeting | bar: 2023-03-02; 2023-03-09; 2023-03-16; 2023-03-23; 2023-03-30; 2023-04-06; 2023-04-13
-above corridor ceilings | bar: 2023-03-02 to 2023-03-03; 2023-03-06 to 2023-03-10; 2023-03-13 to 2023-03-17; 2023-03-20 to 2023-03-24; 2023-03-27 to 2023-03-31; 2023-04-03 to 2023-04-07; 2023-04-10 to 2023-04-14
-corridor framing | bar: 2023-03-03
-plimbging top-out | bar: 2023-03-02 to 2023-03-03; 2023-03-06 to 2023-03-10; 2023-03-13 to 2023-03-17; 2023-03-20 to 2023-03-24; 2023-03-27 to 2023-03-31; 2023-04-03 to 2023-04-07; 2023-04-10 to 2023-04-14
-Area A in-wall/insy/wallboard | bar: 2023-03-08 to 2023-03-10